## Description
COMP 5700/5703/6700/6706 -- Software Process
Assignment: | CA05
5700/6700 due date: | 2012-11-04 | 11:55pm | Central time | Blackout begins | 2012-11-01 | 6pm
6706 due date: | 2012-11-11 | 11:55pm | Central time | Blackout begins | 2012-11-07 | 6pm
Name of this file: | CA05.xls
Objective: | to gain experience with estimating size and effort.
Assignment: | The worksheets in this assignment provide you with a hypothetical historical development database as well as with a forecast of standard components for a hypothetical project. Please use this information to determine the size and effort of the project.
Notes: | - This homework assignment is be accomplished individually
Deliverables: | - This spreadsheet with "Assignment" completed.
- (Optional) Explanatory calculations on worksheets "Calc-1", "Calc-2", etc.
- When complete, upload the spreadsheet to Canvas
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect. Use "comp6700" if a password is requested.

## Process
Process Script
Entry |  | - this spreadsheet
Tasks |  | see lecture notes
Exit |  | - complete "Assignment" worksheet
- (optional) intermediate calculations
Quality checks
General
Are all regions highlighted in yellow complete? (Either with a value, or NA if the cell is not applicable. No units of measure.)
Are supporting calculations understandable?
Size matrix
Are buckets sized by a log-normal distribution?
Component sizing
Has each new component been given a relative size?
Are new components sized according to the size matrix?
Are base components accounted for?
Size calculations
Is effort based on the new and modified components?
Is productivity calcuated in LOC/hr?
Are correlation values based on correct data sets?
Is the range calculation valid? It is correct?
Does the Lower Prediction Interval (LPI) represent a valid value?
Top-down effort calculations
Are the lifecycle activities distributed according to historical performance?
Useful Excel Functions
| correl | parms: | x's, y's
|  | returns: | correlation coefficient
|  | example: | given the data at right, | X | Y
|  |  | "=CORREL(F83:F88,G83:G88)" | 1 | 2
|  |  | yields | 2 | 4
|  |  | 0.98372 | 4 | 8
|  |  |  | 5 | 10
|  |  |  | 6 | 12
|  |  |  | 7 | 17
| average | parms: | values
|  | returns: | average of the values
|  | example: | the average of the x's above is "=AVERAGE(F42:F47)", or |  |  | 4.1667
| stdev | parms: | values
|  | returns: | standard deviation of the values
|  | example: | the std of the x's above is "=STDEV(F42:F47)", or |  |  | 2.3166
| sum | parms: | values
|  | returns: | sum of the values
|  | example: | the sum of the x's above is "=SUM(F42:F47)", which yields |  |  | 25
| ln | parms: | value
|  | returns: | natural logarithm of the value
|  | example: | the natural logarithm of the value above is "=ln(I59)", which yields |  |  | 3.2189
| exp | parms: | power
|  | returns: | 2.718^power
|  | example: | the antilog of the natural log abve "=exp(I59)", which is |  |  | 25
| ceiling | parms: | value, places
|  | returns: | a value that is rounded up to the nearest significant digit
|  | example: | the integer ceiling of 4.1667 is "=ceiling(4.1667,1)", which is: |  |  | 5
| floor | parms: | value, places
|  | returns: | a value that is rounded down to the nearest significant digit
|  | example: | the integer floor of 4.1667 is "=floor(4.1667,1)", which is |  |  | 4

## Component History
Component History: The following is a record of historical components.
| Identifier | Total Loc | Methods | Type
| Component1 | 14 | 1 | Calculation
| Component2 | 152 | 14 | Calculation
| Component3 | 71 | 7 | Data
| Component4 | 341 | 26 | I/O
| Component5 | 19 | 1 | Calculation
| Component6 | 38 | 1 | Logic
| Component7 | 56 | 6 | I/O
| Component8 | 16 | 1 | Data
| Component9 | 224 | 17 | I/O
| Component10 | 296 | 24 | Logic
| Component11 | 225 | 16 | I/O
| Component12 | 82 | 4 | I/O
| Component13 | 28 | 2 | I/O
| Component14 | 19 | 2 | Calculation
| Component15 | 112 | 7 | Logic
| Component16 | 16 | 1 | Data
| Component17 | 235 | 19 | Data
| Component18 | 129 | 10 | Data
| Component19 | 83 | 8 | Data
| Component20 | 104 | 9 | Logic
| Component21 | 139 | 12 | Logic
| Component22 | 77 | 3 | Logic
| Component23 | 23 | 2 | Logic
| Component24 | 209 | 17 | I/O
| Component25 | 33 | 3 | Data
| Component26 | 89 | 5 | I/O
| Component27 | 167 | 13 | I/O
| Component28 | 119 | 11 | Logic
| Component29 | 104 | 7 | Data
| Component30 | 15 | 3 | Data
| Component31 | 42 | 3 | Data
| Component32 | 126 | 11 | Calculation
| Component33 | 117 | 7 | Logic
| Component34 | 106 | 8 | Calculation
| Component35 | 140 | 13 | Calculation
| Component36 | 9 | 1 | Calculation
| Component37 | 194 | 15 | Data
| Component38 | 55 | 8 | Logic
| Component39 | 68 | 3 | Logic
| Component40 | 308 | 24 | Calculation
| Component41 | 124 | 5 | Data
| Component42 | 5 | 1 | I/O
| Component43 | 181 | 17 | Data
| Component44 | 119 | 9 | Logic
| Component45 | 247 | 20 | I/O
| Component46 | 66 | 5 | I/O
| Component47 | 38 | 2 | Calculation
| Component48 | 125 | 8 | I/O
| Component49 | 12 | 2 | Logic
| Component50 | 65 | 5 | Calculation
| Component51 | 141 | 12 | Data
| Component52 | 47 | 1 | Calculation
| Component53 | 72 | 5 | Calculation
| Component54 | 60 | 4 | I/O
| Component55 | 102 | 10 | Calculation
| Component56 | 112 | 9 | Data
| Component57 | 168 | 14 | Data
| Component58 | 25 | 5 | Logic
| Component59 | 164 | 11 | I/O
| Component60 | 37 | 2 | I/O
| Component61 | 57 | 4 | Data
| Component62 | 17 | 1 | Calculation
| Component63 | 176 | 12 | Data
| Component64 | 223 | 18 | Calculation
| Component65 | 26 | 1 | Data
| Component66 | 51 | 6 | I/O
| Component67 | 170 | 14 | Logic
| Component68 | 268 | 18 | Data
| Component69 | 222 | 17 | Logic
| Component70 | 62 | 6 | Calculation
| Component71 | 83 | 7 | Calculation
| Component72 | 219 | 21 | Data
| Component73 | 115 | 10 | Logic
| Component74 | 29 | 4 | Calculation
| Component75 | 108 | 11 | Logic
| Component76 | 152 | 13 | Logic
| Component77 | 52 | 3 | Data
| Component78 | 5 | 1 | Calculation
| Component79 | 196 | 16 | Logic
| Component80 | 82 | 7 | Data
| Component81 | 142 | 11 | Logic
| Component82 | 10 | 2 | Data
| Component83 | 33 | 2 | I/O
| Component84 | 52 | 3 | Logic
| Component85 | 20 | 4 | Logic
| Component86 | 94 | 11 | Calculation
| Component87 | 55 | 0 | Data

## Project History
Project History: The following is a record of actual/estimated performance on past projects. Note: times are in minutes.
| Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea)
| Project1 | 579 | 476 | 647 | 2517 | 2400
| Project2 | 760 | 1138 | 2191 | 2036 | 6139
| Project3 | 369 | 572 | 1186 | 987 | 3564
| Project4 | 397 | 186 | 308 | 1847 | 812
| Project5 | 410 | 808 | 1574 | 3188 | 7486
| Project6 | 1159 | 904 | 1401 | 2988 | 5063
| Project7 | 1534 | 1880 | 3084 | 2904 | 9448
| Project8 | 1884 | 4117 | 8241 | 4810 | 40009
| Project9 | 2357 | 1676 | 2916 | 7593 | 12262
| Project10 | 540 | 643 | 1476 | 2707 | 4321
| Project11 | 1624 | 2254 | 3987 | 3394 | 14047
| Project12 | 1388 | 1658 | 2807 | 7771 | 6884
| Project13 | 1226 | 1816 | 3961 | 4648 | 13927
| Project14 | 526 | 533 | 857 | 1722 | 2376
| Project15 | 1004 | 1492 | 2845 | 3415 | 10562
| Project16 | 859 | 672 | 1331 | 2589 | 4482
| Project17 | 3293 | 2114 | 2915 | 8558 | 9045
| Project18 | 1061 | 1177 | 2769 | 3109 | 7030
| Project19 | 2134 | 2670 | 4551 | 6662 | 11951
| Project20 | 2612 | 2666 | 5138 | 5218 | 15292

## Activities
Activities: The following describes the to-date percentages for development time and defects.
| Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
| Analysis | 13% | 5% | 0%
| Architecture | 10% | 10% | 0%
| Project planning | 1% | 0% | 0%
| Interation Planning | 5% | 0% | 0%
| Construction | 50% | 77% | 30%
| Refactoring | 4% | 3% | 1%
| Review | 1% | 0% | 3%
| Integration Test | 8% | 0% | 66%
| Repatterning | 1% | 0% | 0%
| Postmortem | 3% | 0% | 0%
| Sandbox | 4% | 5% | 0%
| Total | 100% | 100% | 100%

## Architecture
Architecture: The following CRC cards describe the solution.
| Component Name | ForecastedComponent01
| Design Approach | OO
Superclass
| Component Type | Data
| Collaborators | ForecastedComponent02, ForecastedComponent05
| Operations | 5 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component51
| Component Name | ForecastedComponent02
| Design Approach | OO
| Superclass | ForecastedComponent06
| Component Type | Data
| Collaborators | ForecastedComponent03, ForecastedComponent04
| Operations | 7 methods
| Notes | The functionality of this component is available by deleting 17 LOC from, modifying 16 LOC of, and adding 29 LOC to Component82 as well as adding 1 new method(s) to Component82
| Component Name | ForecastedComponent03
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 5 methods
| Notes | The functionality of this component is available by deleting 14 LOC from, modifying 13 LOC of, and adding 21 LOC to Component70 as well as adding 1 new method(s) to Component70
| Component Name | ForecastedComponent04
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 4 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component31
| Component Name | ForecastedComponent05
| Design Approach | FD
Superclass
| Component Type | I/O
Collaborators
| Operations | 1 method
| Notes | The functionality of this component is available by deleting 12 LOC from, modifying 11 LOC of, and adding 20 LOC to Component59.
| Component Name | ForecastedComponent06
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 5 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component58

## COCOMO
COCOMO: The following values are COCOMO reference factors and drivers
|  | Very Low | Low | Nominal | High | Very High | Extra High
Scale Factors
| Precedent | 6.2 | 4.96 | 3.72 | 2.48 | 1.24 | 0
| Flexibility | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0
| Risk resolution | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0
| Team Cohesion | 5.48 | 4.38 | 3.29 | 2.19 | 1.1 | 0
| Process Level | 7.8 | 6.24 | 4.68 | 3.12 | 1.56 | 0
Cost Drivers
Product attributes
| Required software reliability | 0.82 | 0.92 | 1 | 1.1 | 1.26 | 1.26
| Size of application database | 0.94 | 0.94 | 1 | 1.08 | 1.16 | 1.16
| Complexity of the product | 0.7 | 0.85 | 1 | 1.15 | 1.3 | 1.65
Hardware attributes
| Run-time performance constraints | 1 | 1 | 1 | 1.11 | 1.3 | 1.66
| Memory constraints | 1 | 1 | 1 | 1.06 | 1.21 | 1.56
| Volatility of the virtual machine environment | 0.87 | 0.87 | 1 | 1.15 | 1.3 | 1.3
| Required turnabout time | 0.87 | 0.87 | 1 | 1.07 | 1.15 | 1.15
Personnel attributes
| Analyst capability | 1.42 | 1.19 | 1 | 0.85 | 0.71 | 0.71
| Applications experience | 1.22 | 1.1 | 1 | 0.88 | 0.81 | 0.81
| Software engineer capability | 1.34 | 1.15 | 1 | 0.88 | 0.76 | 0.76
| Virtual machine experience | 1.21 | 1.1 | 1 | 0.9 | 0.9 | 0.9
| Programming language experience | 1.14 | 1.07 | 1 | 0.95 | 0.95 | 0.95
| Personnel continuity | 1.29 | 1.1 | 1 | 0.88 | 0.81 | 0.81
Project attributes
| Application of software engineering methods | 1.24 | 1.1 | 1 | 0.91 | 0.82 | 0.82
| Use of software tools | 1.24 | 1.1 | 1 | 0.91 | 0.83 | 0.83
| Required development schedule | 1.23 | 1.08 | 1 | 1.04 | 1.1 | 1.1

## Solution
Name: | Elizabeth Dayton
Username: | ead0044
Instructor Assessment
Aspect | Possible Score | Earned Score | Comment
Size matrix | 15
Component sizing | 15
Size calculations | 20
Bottom-up effort calculations | 20
Top-down effort calculations | 10
Total | 80 | 0
Estimates on New Development: Please provide answers to the questions below. If a result is not calculable, please fill the box with a "NA" and defend your answer in the supporting calculations section. Each cell should contain a number, "NA", or a value from a drop-down menu; do not indicate units (such as "min", "hr", "LOC", etc.) Please do not leave any boxes blank; I will assume that an empty box means you did not answer the question.
Parameters
normal | Day 1
log-normal | Day 2
not applicable | Day 3
LOCE x Time | Day 4
LOCA x Time | Day 5
Productivity | Day 6
not applicable | Day 7
VS | Day 8
S | Day 9
M | Day 10
L | Day 11
VL | Day 12
not applicable | Day 13
Calculation | Day 14
Data | Day 15
IO | Day 16
Logic | Day 17
not applicable | Day 18
low | Day 19
medium | Day 20
high | Day 21
Decision D | Day 22
not applicable | Day 23
Day 24
Day 25
Day 26
Day 27
Day 28
Day 29
Day 30
Day 31
Never
Solution
Size matrix
| Low | Mid | High
VS | 1 | 6 | 7 | LOC/Method
S | 7 | 8 | 10 | LOC/Method
M | 10 | 13 | 15 | LOC/Method
L | 15 | 19 | 23 | LOC/Method
VL | 23 | 28 | Big | LOC/Method
Component sizing
Component | Raw New LOC
ForecastedComponent01 | 60 | LOC
ForecastedComponent02 | 50 | LOC
ForecastedComponent03 | 44 | LOC
ForecastedComponent04 | 56 | LOC
ForecastedComponent05 | 31 | LOC
ForecastedComponent06 | 25 | LOC
Size calculations
Total raw size (LOCr) | 266 | LOC
Planned size (LOCp) | 560 | LOC
Lower prediction interval (LPI) | 206 | LOC
Upper prediction interval (UPI) | 1164 | LOC
Confidence | low
Bottom-up effort calculations
Productivity (Prod) | 17 | LOC/hr
Planned effort (Ep) | 1934 | Minutes
Lower prediction interval (LPI) | 1373 | Minutes
Upper prediction interval (UPI) | 2719 | Minutes
Confidence | low
How much overall effort do you anticipate expending in construction? | 967 | Minutes
Top-down effort calculations
Person months, if all factors are nominal: | 1.5539 | Person Months
Person months, worst case: |  | Person Months
Person months, best case: | 0.1605 | Person Months

## Calc-1
Supporting Calculations for
Size matrix
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component1 | 14 | 1 | Calculation | 14 | 2.6391 | M
Component2 | 152 | 14 | Calculation | 10.8571 | 2.3848 | M
Component3 | 71 | 7 | Data | 10.1429 | 2.3168 | M
Component4 | 341 | 26 | I/O | 13.1154 | 2.5738 | M
Component5 | 19 | 1 | Calculation | 19 | 2.9444 | L
Component6 | 38 | 1 | Logic | 38 | 3.6376 | VL | Avg = | 2.5264
Component7 | 56 | 6 | I/O | 9.3333 | 2.2336 | S | Std = | 0.40444
Component8 | 16 | 1 | Data | 16 | 2.7726 | L
Component9 | 224 | 17 | I/O | 13.1765 | 2.5784 | M
Component10 | 296 | 24 | Logic | 12.3333 | 2.5123 | M |  | Low | Mid | High
Component11 | 225 | 16 | I/O | 14.0625 | 2.6435 | M | VS | 1 | 6 | 7 | LOC/Method
Component12 | 82 | 4 | I/O | 20.5 | 3.0204 | L | S | 7 | 8 | 10 | LOC/Method
Component13 | 28 | 2 | I/O | 14 | 2.6391 | M | M | 10 | 13 | 15 | LOC/Method
Component14 | 19 | 2 | Calculation | 9.5 | 2.2513 | M | L | 15 | 19 | 23 | LOC/Method
Component15 | 112 | 7 | Logic | 16 | 2.7726 | L | VL | 23 | 28 | Big | LOC/Method
Component16 | 16 | 1 | Data | 16 | 2.7726 | L
Component17 | 235 | 19 | Data | 12.3684 | 2.5151 | M
Component18 | 129 | 10 | Data | 12.9 | 2.5572 | M | For low column
Component19 | 83 | 8 | Data | 10.375 | 2.3394 | M | S = e^(average-1.5*std) |  |  | 6.8192 |  | rounded this is 7
Component20 | 104 | 9 | Logic | 11.5556 | 2.4472 | M | M=e^(average-0.5*std) |  |  | 10.2184 |  | rounded this is 10
Component21 | 139 | 12 | Logic | 11.5833 | 2.4496 | M | L=e^(average+0.5*std) |  |  | 15.3119 |  | rounded this is 15
Component22 | 77 | 3 | Logic | 25.6667 | 3.2452 | VL | VL=e^(average+1.5*std) |  |  | 22.9444 |  | rounded this is 23
Component23 | 23 | 2 | Logic | 11.5 | 2.4423 | M
Component24 | 209 | 17 | I/O | 12.2941 | 2.5091 | M
Component25 | 33 | 3 | Data | 11 | 2.3979 | M | For mid column
Component26 | 89 | 5 | I/O | 17.8 | 2.8792 | L | VS=e^(average-2*std) |  |  | 5.5707 |  | rounded this is 6
Component27 | 167 | 13 | I/O | 12.8462 | 2.553 | M | S=e^(average-std) |  |  | 8.3475 |  | rounded this is 8
Component28 | 119 | 11 | Logic | 10.8182 | 2.3812 | M | M=e^(average) |  |  | 12.5085 |  | rounded this is 13
Component29 | 104 | 7 | Data | 14.8571 | 2.6985 | M | L=e^(average+std) |  |  | 18.7436 |  | rounded this is 19
Component30 | 15 | 3 | Data | 5 | 1.6094 | VS | VL=e^(average+2*std) |  |  | 28.0867 |  | rounded this is 28
Component31 | 42 | 3 | Data | 14 | 2.6391 | M
Component32 | 126 | 11 | Calculation | 11.4545 | 2.4384 | M | For high column
Component33 | 117 | 7 | Logic | 16.7143 | 2.8163 | L | VS=e^(average-1.5*std) |  |  | 6.8192 |  | rounded this is 7
Component34 | 106 | 8 | Calculation | 13.25 | 2.584 | M | S=e^(average-0.5*std) |  |  | 10.2184 |  | rounded this is 10
Component35 | 140 | 13 | Calculation | 10.7692 | 2.3767 | M | M=e^(average+0.5*std) |  |  | 15.3119 |  | rounded this is 15
Component36 | 9 | 1 | Calculation | 9 | 2.1972 | S | L=e^(average+1.5*std) |  |  | 22.9444 |  | rounded this is 23
Component37 | 194 | 15 | Data | 12.9333 | 2.5598 | M
Component38 | 55 | 8 | Logic | 6.875 | 1.9279 | VS
Component39 | 68 | 3 | Logic | 22.6667 | 3.1209 | VL
Component40 | 308 | 24 | Calculation | 12.8333 | 2.552 | M
Component41 | 124 | 5 | Data | 24.8 | 3.2108 | VL
Component42 | 5 | 1 | I/O | 5 | 1.6094 | VS
Component43 | 181 | 17 | Data | 10.6471 | 2.3653 | M
Component44 | 119 | 9 | Logic | 13.2222 | 2.5819 | M
Component45 | 247 | 20 | I/O | 12.35 | 2.5137 | M
Component46 | 66 | 5 | I/O | 13.2 | 2.5802 | M
Component47 | 38 | 2 | Calculation | 19 | 2.9444 | L
Component48 | 125 | 8 | I/O | 15.625 | 2.7489 | L
Component49 | 12 | 2 | Logic | 6 | 1.7918 | VS
Component50 | 65 | 5 | Calculation | 13 | 2.5649 | M
Component51 | 141 | 12 | Data | 11.75 | 2.4639 | M
Component52 | 47 | 1 | Calculation | 47 | 3.8501 | VL
Component53 | 72 | 5 | Calculation | 14.4 | 2.6672 | M
Component54 | 60 | 4 | I/O | 15 | 2.7081 | L
Component55 | 102 | 10 | Calculation | 10.2 | 2.3224 | M
Component56 | 112 | 9 | Data | 12.4444 | 2.5213 | M
Component57 | 168 | 14 | Data | 12 | 2.4849 | M
Component58 | 25 | 5 | Logic | 5 | 1.6094 | VS
Component59 | 164 | 11 | I/O | 14.9091 | 2.702 | L
Component60 | 37 | 2 | I/O | 18.5 | 2.9178 | L
Component61 | 57 | 4 | Data | 14.25 | 2.6568 | M
Component62 | 17 | 1 | Calculation | 17 | 2.8332 | L
Component63 | 176 | 12 | Data | 14.6667 | 2.6856 | L
Component64 | 223 | 18 | Calculation | 12.3889 | 2.5168 | M
Component65 | 26 | 1 | Data | 26 | 3.2581 | VL
Component66 | 51 | 6 | I/O | 8.5 | 2.1401 | S
Component67 | 170 | 14 | Logic | 12.1429 | 2.4967 | M
Component68 | 268 | 18 | Data | 14.8889 | 2.7006 | L
Component69 | 222 | 17 | Logic | 13.0588 | 2.5695 | M
Component70 | 62 | 6 | Calculation | 10.3333 | 2.3354 | M
Component71 | 83 | 7 | Calculation | 11.8571 | 2.4729 | M
Component72 | 219 | 21 | Data | 10.4286 | 2.3445 | M
Component73 | 115 | 10 | Logic | 11.5 | 2.4423 | M
Component74 | 29 | 4 | Calculation | 7.25 | 1.981 | S
Component75 | 108 | 11 | Logic | 9.8182 | 2.2842 | M
Component76 | 152 | 13 | Logic | 11.6923 | 2.4589 | M
Component77 | 52 | 3 | Data | 17.3333 | 2.8526 | L
Component78 | 5 | 1 | Calculation | 5 | 1.6094 | VS
Component79 | 196 | 16 | Logic | 12.25 | 2.5055 | M
Component80 | 82 | 7 | Data | 11.7143 | 2.4608 | M
Component81 | 142 | 11 | Logic | 12.9091 | 2.5579 | M
Component82 | 10 | 2 | Data | 5 | 1.6094 | VS
Component83 | 33 | 2 | I/O | 16.5 | 2.8034 | L
Component84 | 52 | 3 | Logic | 17.3333 | 2.8526 | L
Component85 | 20 | 4 | Logic | 5 | 1.6094 | VS
Component86 | 94 | 11 | Calculation | 8.5455 | 2.1454 | S
Component87 | 55 | 0 | Data | No methods so this is ignored

## Calc-2
Supporting Calculations for
Component sizing
Architecture |  | Estimation Basis | Relative Size | Modified LOC | Added LOC | Deleted LOC | Base LOC | New Methods | LOC/Method | New LOC | Totals
ForecastedComponent01 |  | Component51 | M | 0 | 0 | 0 | 0 | 5 | 12 | 60 | 60
ForecastedComponent02 |  | Component82 | VS | 16 | 29 | 17 | 45 | 1 | 5 | 5 | 50
ForecastedComponent03 |  | Component70 | M | 13 | 21 | 14 | 34 | 1 | 10 | 10 | 44
ForecastedComponent04 |  | Component31 | M | 0 | 0 | 0 | 0 | 4 | 14 | 56 | 56
ForecastedComponent05 |  | Component59 | L | 11 | 20 | 12 | 31 | 0 | 0 | 0 | 31
ForecastedComponent06 |  | Component58 | VS | 0 | 0 | 0 | 0 | 5 | 5 | 25 | 25
ForecastedComponent01 is most similar in complexity to Component51 so we will use it to estimate
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component51 | 141 | 12 | Data | 11.75 | 2.4639 | M
ForecastedComponent02 is created by modifiying some of Component82 and adding another method to Component82
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component82 | 10 | 2 | Data | 5 | 1.6094 | VS
ForecastedComponent03 is created by modifiying some of Component70 and adding another method to Component70
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component70 | 62 | 6 | Calculation | 10.3333 | 2.3354 | M
ForecastedComponent04 is most similar in complexity to Component31 so we will use it to estimate
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component31 | 42 | 3 | Data | 14 | 2.6391 | M
ForecastedComponent05 is created by modifiying some of Component59
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component59 | 164 | 11 | I/O | 14.9091 | 2.702 | L
ForecastedComponent06 is most similar in complexity to Component58 so we will use it to estimate
Identifier | Total Loc | Methods | Type | LOC/Method | ln(LOC/Method) | Relative Size
Component58 | 25 | 5 | Logic | 5 | 1.6094 | VS

## Calc-3
Supporting calculations for
Size calculations
Architecture |  | Estimation Basis | Relative Size | Modified LOC | Added LOC | Deleted LOC | Base LOC | New Methods | LOC/Method | New LOC | Totals
ForecastedComponent01 |  | Component51 | M | 0 | 0 | 0 | 0 | 5 | 12 | 60 | 60
ForecastedComponent02 |  | Component82 | VS | 16 | 29 | 17 | 45 | 1 | 5 | 5 | 50
ForecastedComponent03 |  | Component70 | M | 13 | 21 | 14 | 34 | 1 | 10 | 10 | 44
ForecastedComponent04 |  | Component31 | M | 0 | 0 | 0 | 0 | 4 | 14 | 56 | 56
ForecastedComponent05 |  | Component59 | L | 11 | 20 | 12 | 31 | 0 | 0 | 0 | 31
ForecastedComponent06 |  | Component58 | VS | 0 | 0 | 0 | 0 | 5 | 5 | 25 | 25
[10 empty] | Total LOCr: | 266
Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea) | LOCa/LOCr
Project1 | 579 | 476 | 647 | 2517 | 2400 | 1.1174
Project2 | 760 | 1138 | 2191 | 2036 | 6139 | 2.8829
Project3 | 369 | 572 | 1186 | 987 | 3564 | 3.2141
Project4 | 397 | 186 | 308 | 1847 | 812 | 0.77582
Project5 | 410 | 808 | 1574 | 3188 | 7486 | 3.839
Project6 | 1159 | 904 | 1401 | 2988 | 5063 | 1.2088
Project7 | 1534 | 1880 | 3084 | 2904 | 9448 | 2.0104
Project8 | 1884 | 4117 | 8241 | 4810 | 40009 | 4.3742
Project9 | 2357 | 1676 | 2916 | 7593 | 12262 | 1.2372
Project10 | 540 | 643 | 1476 | 2707 | 4321 | 2.7333
Project11 | 1624 | 2254 | 3987 | 3394 | 14047 | 2.455
Project12 | 1388 | 1658 | 2807 | 7771 | 6884 | 2.0223
Project13 | 1226 | 1816 | 3961 | 4648 | 13927 | 3.2308
Project14 | 526 | 533 | 857 | 1722 | 2376 | 1.6293
Project15 | 1004 | 1492 | 2845 | 3415 | 10562 | 2.8337
Project16 | 859 | 672 | 1331 | 2589 | 4482 | 1.5495
Project17 | 3293 | 2114 | 2915 | 8558 | 9045 | 0.88521
Project18 | 1061 | 1177 | 2769 | 3109 | 7030 | 2.6098
Project19 | 2134 | 2670 | 4551 | 6662 | 11951 | 2.1326
Project20 | 2612 | 2666 | 5138 | 5218 | 15292 | 1.9671 |  | min = 0.77581864
max = 4.374203822
Sum of LOCa: | 54185
Sum of LOCr: | 25716 | [6 empty] | LPI : | 206 |  | this is calculated by taking the floor of LOCr*min
[8 empty] | UPI : | 1164 |  | this is calculated by taking the ceiling of LOCr*max
Ratio of LOCa to LOCr is |  | 2.1071 | [5 empty] | Confidence : | 0.40388 | which is low | this is calculated by calculating the correlation between the columns of LOCr and LOCa and squaring it
We then multiply this by our original calculated LOCr and get: |  |  |  | 560.4764 | planned lines of code

## Calc-4
Supporting Calculations for
Bottom-up effort calculations
Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea) | LOCa/LOCr | Ea/LOCa
Project1 | 579 | 476 | 647 | 2517 | 2400 | 1.1174 | 3.7094
Project2 | 760 | 1138 | 2191 | 2036 | 6139 | 2.8829 | 2.8019
Project3 | 369 | 572 | 1186 | 987 | 3564 | 3.2141 | 3.0051
Project4 | 397 | 186 | 308 | 1847 | 812 | 0.77582 | 2.6364
Project5 | 410 | 808 | 1574 | 3188 | 7486 | 3.839 | 4.756
Project6 | 1159 | 904 | 1401 | 2988 | 5063 | 1.2088 | 3.6138
Project7 | 1534 | 1880 | 3084 | 2904 | 9448 | 2.0104 | 3.0636
Project8 | 1884 | 4117 | 8241 | 4810 | 40009 | 4.3742 | 4.8549
Project9 | 2357 | 1676 | 2916 | 7593 | 12262 | 1.2372 | 4.2051
Project10 | 540 | 643 | 1476 | 2707 | 4321 | 2.7333 | 2.9275
Project11 | 1624 | 2254 | 3987 | 3394 | 14047 | 2.455 | 3.5232
Project12 | 1388 | 1658 | 2807 | 7771 | 6884 | 2.0223 | 2.4524
Project13 | 1226 | 1816 | 3961 | 4648 | 13927 | 3.2308 | 3.516
Project14 | 526 | 533 | 857 | 1722 | 2376 | 1.6293 | 2.7725
Project15 | 1004 | 1492 | 2845 | 3415 | 10562 | 2.8337 | 3.7125
Project16 | 859 | 672 | 1331 | 2589 | 4482 | 1.5495 | 3.3674
Project17 | 3293 | 2114 | 2915 | 8558 | 9045 | 0.88521 | 3.1029
Project18 | 1061 | 1177 | 2769 | 3109 | 7030 | 2.6098 | 2.5388
Project19 | 2134 | 2670 | 4551 | 6662 | 11951 | 2.1326 | 2.626
Project20 | 2612 | 2666 | 5138 | 5218 | 15292 | 1.9671 | 2.9763
Sum of LOCa: | 54185 |  |  |  |  | min = 0.77581864 | min = 2.452440328
Sum of LOCr: | 25716 |  |  |  |  | max = 4.374203822 | max = 4.854871982 | LPI : | 1373 |  | this is calculated by taking the floor of min(Ea/LOCa)*LOCp
Sum of Ea: | 187100 | [6 empty] | UPI : | 2719 |  | this is calculated by taking the ceiling of max(Ea/LOCa)*LOCp
[8 empty] | Confidence : | 0.89364 | which is high | this is calculated by calculating the correlation between the columns of LOCa and Ea and squaring it
The confidence for effort is the minimum of this and the size confidence, so since this is high and the size confidence is low, we will make the value for effort low
We then multiply this by our original calculated LOCr and get: |  |  |  | 560 | planned lines of code |  |  | Ratio of Ea to LOCa: |  | 3.453
[8 empty] | Productivity : | 17.3763 |  | this is calculated by calculated 1/the ratio of Ea to LOCa and then multiplying by 60
[8 empty] | Ep : | 1933.6717 |  | this is calculated by multiplying the above ration by LOCp
Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
Analysis | 13% | 5% | 0%
Architecture | 10% | 10% | 0%
Project planning | 1% | 0% | 0%
Interation Planning | 5% | 0% | 0%
Construction | 50% | 77% | 30% |  | According this graph, we inted to spend 50% of our time on construction which means we plan to spend | [5 empty] | 966.8358 | minutes on construction
Refactoring | 4% | 3% | 1%
Review | 1% | 0% | 3%
Integration Test | 8% | 0% | 66%
Repatterning | 1% | 0% | 0%
Postmortem | 3% | 0% | 0%
Sandbox | 4% | 5% | 0%
Total | 100% | 100% | 100%

## Calc-5
Supporting Calculations for
Top-down effort calculations
| Very Low | Low | Nominal | High | Very High | Extra High
Scale Factors
Precedent | 6.2 | 4.96 | 3.72 | 2.48 | 1.24 | 0
Flexibility | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0 | LOCp = 560
Risk resolution | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0
Team Cohesion | 5.48 | 4.38 | 3.29 | 2.19 | 1.1 | 0
Process Level | 7.8 | 6.24 | 4.68 | 3.12 | 1.56 | 0 | PM = A * Size^(B+0.01*sumOfScaleFactors) * product(EM)
Cost Drivers | [6 empty] | A = calibration data = | 2.94
Product attributes | [6 empty] | B = calibration data = | 0.91
Required software reliability | 0.82 | 0.92 | 1 | 1.1 | 1.26 | 1.26 | EM = effort multipliers = | nominal : | 1 | best case: | 0.092549
Size of application database | 0.94 | 0.94 | 1 | 1.08 | 1.16 | 1.16 | Size = LOCp/1000 = | 0.56
Complexity of the product | 0.7 | 0.85 | 1 | 1.15 | 1.3 | 1.65 | SF = scaleFactors = | nominal : | 18.97 | best case: | 0
Hardware attributes
Run-time performance constraints | 1 | 1 | 1 | 1.11 | 1.3 | 1.66
Memory constraints | 1 | 1 | 1 | 1.06 | 1.21 | 1.56
Volatility of the virtual machine environment | 0.87 | 0.87 | 1 | 1.15 | 1.3 | 1.3 | PM for nominal case = | 1.5539
Required turnabout time | 0.87 | 0.87 | 1 | 1.07 | 1.15 | 1.15 | PM for best case = | 0.16053
Personnel attributes
Analyst capability | 1.42 | 1.19 | 1 | 0.85 | 0.71 | 0.71
Applications experience | 1.22 | 1.1 | 1 | 0.88 | 0.81 | 0.81
Software engineer capability | 1.34 | 1.15 | 1 | 0.88 | 0.76 | 0.76
Virtual machine experience | 1.21 | 1.1 | 1 | 0.9 | 0.9 | 0.9
Programming language experience | 1.14 | 1.07 | 1 | 0.95 | 0.95 | 0.95
Personnel continuity | 1.29 | 1.1 | 1 | 0.88 | 0.81 | 0.81
Project attributes
Application of software engineering methods | 1.24 | 1.1 | 1 | 0.91 | 0.82 | 0.82
Use of software tools | 1.24 | 1.1 | 1 | 0.91 | 0.83 | 0.83
Required development schedule | 1.23 | 1.08 | 1 | 1.04 | 1.1 | 1.1